## Sheet2
MCI Project Weekly Time Sheet
Team | 5 | Student ID a1779388 |  |  |  | Week starting: Week 11 2021/5/10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-10 | 15:00 | 19:00 | 4 | We had a regular group meeting online. | Discuss about the code error in our project. | some issues related to PHP need to be modified.
Tuesday | 2021-05-11 | 18:00 | 22:00 | 4 | Keep learning PHP and database to finish our task | PHP is a essential language in this code file. | Some problems related to PHP and database are being processed.
Wednesday | 2021-05-12 | 14:00 | 18:00 | 4 | Have the workshope session which is one to one session. | Received some feedback from the professor | Modify our next plan and have some ideas about what to improve. We should have our plan more detailed in the final report and in our next progress.
Thursday | 2021-05-13 | 10:00 | 14:00 | 4 | We had a meeting with our client. | Meeting the client can help us know what need to be done next and what need to be improved | The client suggested that we should have some feedback function in our project and we should modify our basic coding structure.
Friday | 2021-05-14 | 16:00 | 21:00 | 5 | Keep working on the user interface part and database part with PHP. | Based on the advice from the client we should modify the basic structure of our webpage. | Working on the database part with PHP. We may need to rewrite the database part.
Saturday | 2021-05-15 | 9:00 | 13:00 | 4 | keep working on the code. | based on the opinion of client, improve and modify the code. | keep working to meet the mile stone.
|  |  | Total | 25