## Sheet2
MCI Project Weekly Time Sheet
Team | 5 | Student ID a1776937 |  |  |  | Week starting: Week 6 2021/4/5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-05 | 14:00 | 18:00 | 4 | we have a group meeting about what we need to do this week. | we sign the tasks about each part. | after that, we can start to write.
Tuesday | 2021-04-06 | 13:00 | 17:00 | 4 | watch the record of the lecture, look up the pictures we can use in our website. | lecture is about how we manage the website. | the interface we design can make this website more pretty.
Wednesday | 2021-04-07 | 14:00 | 18:00 | 4 | I write this week agenda about tomorrow's meeting. After that, I sent a email to the clients. | I make some points about what we need to discuss in meeting. | we arrange the fifth meeting with clients
Thursday | 2021-04-08 | 14:00 | 18:00 | 4 | we have a meeting with clients, make sure the few steps we need to do in the mid-break. | this arrangement is for everyone to write the code. | after that, we will start this website.
Friday | 2021-04-09 | 13:00 | 18:00 | 5 | begin writing the front end code. | code is the foundation of this website. | I still need to learn more knowledge.
Saturday | 2021-04-10 | 11:00 | 15:00 | 4 | I review this week arrangement. And plan for the new week. | arrangement is very important. | we can still use the time of mid-break to design the website.
|  |  | Total | 25