## Sheet2
MCI Project Weekly Time Sheet
Team | 5 | Student ID a1776937 |  |  |  | Week starting: Week 3 2021/3/15
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-15 | 15:00 | 19:00 | 4 | watching lecture and finding some websites which are similar with our projects. | We need to find some ideas about how to build up our website. | I learn a lot of knowledge in the lecture, and share some websites with our team members.
Tuesday | 2021-03-16 | 11:00 | 17:00 | 6 | I wrote agenda about this week's meeting. After that, I study how to write code in this project. | Discuss some questions about this week's meeting is important. | I sent the agenda into the Github.
Wednesday | 2021-03-17 | 14:00 | 18:00 | 4 | the second meeting with our team numbers. Discuss how we communicate with clients tomorrow. After that, I also learn some knowledge about website. | We distributed taks in the pitch presentation, and discuss some details about that. | We have an initial plan about the PPT of Pitch presentation.
Thursday | 2021-03-18 | 14:00 | 17:00 | 4 | reschedual the meeting time with clients. And revise the agenda, after that, upload it into the github. | it's the first time we write agenda. it can let the clients know what are we going to talk about in the next meeting. | we write some questions in the agenda, and also put some picture of websites that suitable for our project.
Friday | 2021-03-19 | 8:00 | 13:00 | 5 | the second meeting with the clients. After that, we write the minute of this week. | the clients tell us some details about the detailed function we need to achieve, and arrange the pitch' task. | task allocation in the next week. We sort out the meeting's details.
Saturday | 2021-03-20 | 11:00 | 15:00 | 4 | I started to learn the necessary steps to draw a flowchart, previewed some project designs, and started preparing for the pitch next week. | pitch presentation is very important for this project. | We need to plan the goals at the beginning of the project, so that we can do better in the future.
|  |  | Total | 27