## Sheet2
MCI Project Weekly Time Sheet
Team | 5 | Student ID a1779388 |  |  |  | Week starting: Week 12 2021/5/17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-17 | 16:00 | 20:00 | 4 | We had a regular group meeting online and start to do the coding work. | Discuss about coming work this week and discuss about what should be done and wha has been done.Keep woring on the database part of coding. | we should add about 4 main function in the coming week to meet the client need.
Tuesday | 2021-05-18 | 18:00 | 22:00 | 4 | Watch the lectue and finish the coding work | The database part in our code should be done so we can start to modify other specific funtion. | Solve problems relaed to database.
Wednesday | 2021-05-19 | 13:00 | 17:00 | 4 | Finish the testing plan. | It is a important part related to our whole project and we should make a specific plan to make sure we can have a successful and complete product. | Make some progress of the testing plan and we will continue to do it on google drive.
Thursday | 2021-05-20 | 10:00 | 14:00 | 4 | We had a meeting with our client. | Meeting the client can help us know what need to be done next and what need to be improved | The client suggested that we should have some register function in our project and we should have a function to reject proposals as administrators. we should have a function to review and leave some comment on the proposals.
Friday | 2021-05-21 | 17:00 | 22:00 | 4 | Working on the meeting minute and submit. | upload the meeting minute and we should keep working to finish the specific funtions that our clietn suggested. | Finish the minute and submit it. Keep working on the register function and "reject" funciton in our code
Saturday | 2021-05-22 | 9:00 | 13:00 | 4 | keep working on the testing plan and continue to work on the register function in our coding. | Testing plan is due soon and we should have multiple check to make sure it is a perfect work. | keep working to meet the client need which are indicated on Thursday.
|  |  | Total | 24