## Sheet2
MCI Project Weekly Time Sheet
Team | 5 | Student ID a1779388 |  |  |  | Week starting: Week 2 2021/3/9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-09 | 14:00 | 17:00 | 3 | (Public Holiday)Communicate with teammates. | Building a better communication with my teammates is good for the future work in the project. | Successully contact teammates and build communication ways with teammates/Discuss basic concept of the project and the way we contact our clients.
Tuesday | 2021-03-10 | 11:00 | 17:00 | 6 | Dicuss the potential questions in this project and prepare to ask the client in the future meeting. | We still have several doubts about the project and identifying them is a good start. | Conducted a list of some potential questions and prepare them for the first meetingl with our client.
Wednesday | 2021-03-11 | 13:00 | 17:00 | 3 | 1.Contact our client via emails to get prepared for the first meeting. 2.First workshop about the oral skills of pitch presentation | First meeting with the clients is a good start to make detailed plans. Learing skills for the pitch. | 1.Send emails to the client and the first meeting was set up on Thursday 4:30.updated/Preparing for the meeting 2. learn some Oral skills.
Thursday | 2021-03-12 | 13:00 | 17:00 | 4 | First meeting with our client. | Having the first meeting to know the user requirement. | Meet with Dr.Alex and Dr.Vivian to conduct some basic idea about hte project. First milestone have been set.
Friday | 2021-03-13 | 8:00 | 12:00 | 4 | 1.discuss about the first milestone with teammates. 2. distribute individual roles in the group 3. Finish the first minute for the first meeting. | Making sure every teammate has even work in this project is important. | 1.Finish the minute 2. distribute roles in the group for the first week. 3.make a plan for next week.
Saturday | 2021-03-14 | 8:00 | 15:00 | 7 | 1.Finish individual timesheet. 2.Do some researches about similar systems and softwares. 3.Upload minute to github | This is the first milestone for next week | The features that we will use have been determined. Finish the first minute and upload it. Upload team minute.
|  |  | Total | 27