## Sheet2
MCI Project Weekly Time Sheet
Team | 5 | Student ID a1778478 |  |  |  | Week starting: Week 2 2021/3/9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-09 | 14:00 | 17:00 | 3 | (Public Holiday)Connecting each other and build communication with each of the teammates | Forming the team and building connection is essential for the project | Successully contacted with each other and built stable communication/Discuss about the project and contact our clients
Tuesday | 2021-03-10 | 11:00 | 17:00 | 6 | Group discussion on the potential questions for the project | Identifying the questions of the project is important for us to get information from the clients | Successfully listed some of the questions and had some further understanding of the project/Contacting our clients
Wednesday | 2021-03-11 | 13:00 | 18:30 | 4.5 | 1.Contacting the clients through emails to set up for the first meeting 2.Having workshop on the oral skills of pitch presentation | Meeting with the clients is the starting point of the plan Learing skills for the pitching. | 1.Emails sent to the client and the first meeting was set up on Thursday 4:30 and due the changes of the clients, the contact info has been updated/Preparing for the meeting 2. Oral skills have been learned.
Thursday | 2021-03-12 | 13:30 | 17:00 | 3.5 | Preparing and having the first meeting with our clients | Having the first meeting to set up future plans | Met with Dr.Alex and Dr.Vivian successfully and had a brief idea about the project Early milestones have been set/Doing research on project proposal engines and softwares that have already been used and building communications with clients.
Friday | 2021-03-13 | 12:00 | 16:00 | 4 | 1.Making plans and milestones for the project 2. Determining roles for the group 3. Organize the minute for the first meeting | Setting up the milestones and balancing the works of each teammmember is important | 1.minute has been made 2. Roles have been determined for this week 3.Plans for next week has been set
Saturday | 2021-03-14 | 11:00 | 18:00 | 7 | Doing research on the similar system and softwares that we will make | This is the first milestone set for next week | Some similar webs have been found and the features that we will be using have been determined/doing further researches and making palns for future moves
|  |  | Total | 28