## Sheet2
MCI Project Weekly Time Sheet
Team | 5 | Student ID a1779388 |  |  |  | Week starting: Week 6 2021/4/5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-05 | 1:00 | 17:00 | 4 | A meeting within the group. The team members discuss the code work that needs to be done | Suggestions from team members are of great help to the smooth progress of the project, and team members should communicate their ideas more frequently. | We discussed how to carry on the work efficiently in the few next weeks.
Tuesday | 2021-04-06 | 12:00 | 16:00 | 4 | Watch the lecture on Monday Find the materials for website in our project | Get prepared for the following code work. | For the coding work, we need to learn more about the tools.
Wednesday | 2021-04-07 | 12:00 | 14:00 | 4 | Find the materials for website in our project and start the coding work | Get the coding work started early can help to meet the milestone successfully | We should look for more successful examples like our project, which will help to make the user interface look better. Next, I should speed up the efficiency of coding work.
Thursday | 2021-04-08 | 8:00 | 12:00 | 3 | client meeting and review the agenda. | Meeting with client can help us to make a specific plan about the future work | Agenda was conducted and reviewed. Agenda was uploaded to Github. ask the client about some doubt about our project, and get feedback from the client.
Friday | 2021-04-09 | 12:00 | 16:00 | 4 | Start working on the front end code | To meet the milestone in the project | Master some basic methods to be familiar with the code tasks to be completed, and plan and arrange the work for mid-break.
Saturday | 2021-04-10 | 12:00 | 18:00 | 6 | Start working on the front end code And make a plan for what I need to do in the coming week. | To meet the milestone in the project | Master some basic methods to be familiar with the code tasks to be completed, and plan and arrange the work for mid-break.
|  |  | Total | 25